## FDAP Gates >>>
Lifecycle Phases
FDAP Gate and Step Submission Points
Purpose
Based on the FDAP, the following template has been developed to fufill Gate and Step submission requirements and securing approval for these requirements at each submission point. This approach ensures a structured progression to the next gate and step in the process.
FDAP Step/Gate Form Submission Process Instructions
This checklist is designed to guide the submission and review process for FDAP steps and gate reviews. Please follow the instructions below:
Step Checklist Submission
1. The checklist must be completed by the Service Provider for each step. 2. The Service Provider will submit the checklist as a signed PDF, along with all relevant materials. 3. The SLTC team will review the submission and add comments directly to the PDF.
Gate Checklist Submission
1. The gate checklist follows the same submission process: completed by the Service Provider, submitted as a signed PDF with supporting materials. 2. During the gate meeting, the Service Provider and Project Manager (PM) are responsible for taking notes and capturing action items. 3. After the meeting, the Service Provider or PM must confirm with SLTC that the notes and actions were accurately captured. 4. Once confirmed, the SLTC will sign the updated document as a PDF to formalize the Gate approval.

## Step 1 PM Selection
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 1 REVIEW: PROJECT MANAGER SELECTION
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 1 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Documentation associated with the recommended Project Manager including: 1. Selection process undertaken 2. Evidence of necessary qualifications as per Project Manager Qualifications and Scope of Work (Appendix D) 3. Evidence of best value for the project 4. Three references associated with the proponent's relevant projects
3 | Copy of the proposed contract with the recommended Project Manager, as per the Project Manager Qualifications and Scope of Work (see Appendix D)
3 | Completed G0 Stage Gate Meeting
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 2 Project Team Selection
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 2 REVIEW: PROJECT TEAM SELECTION AND PRELIMINARY SITE SELECTION
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 2 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Documentation associated with the recommended Project Team including: 1. Selection process undertaken 2. Evidence of necessary qualifications as per Project Team Qualifications and Scope of Work (see Appendix E) 3. Evidence of best value for the project 4. Three references associated with the proponent's relevant projects
3 | Copy of the proposed contract with the recommended Prime Design Consultant
4 | Copy(s) of the proposed contracts with the other consultants, as available
5 | Preliminary Site Selection Summary
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 3 Functional Program
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 3 REVIEW: FUNCTIONAL PROGRAM
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 3 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Preliminary Project Plan and Charter (see Appendix G)
3 | Functional Program Package
4 | Recommended Preferred Site for the Facility
5 | Preliminary Total Capital Budget, as captured in the IPMP (see Appendix B)
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 4 Concept Design
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 4 REVIEW: CONCEPT DESIGN
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 4 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Conceptual Design Package
3 | Space Comparison Table (see Appendix I)
4 | Mechanical System Energy Evaluation
5 | Final evaluations of the preferred site
6 | Commissioning Agent Engagement Contract
7 | Preliminary Commissioning Plan Submission
8 | Construction Manager Contract (if applicable)
9 | Updated Total Capital Budget (see Appendix B)
11 | Class D Construction Estimate
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Gate 4 Approval Detailed Design
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
GATE 4: APPROVAL DETAILED DESIGN
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Approved Step 4 FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Complete Gate 4 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
3 | Presentation of latest scope, cost, schedule and risk status
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the Gate if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
GATE APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Gate.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Associate Deputy Minister
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Executive Director
DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date
Project Executive
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 5 Schematic Design
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 5 REVIEW: SCHEMATIC DESIGN
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 5 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Schematic Design Package
3 | Updated Space Comparison Table (see Appendix I)
4 | Proposed Mechanical and Electrical System
5 | Preliminary Start-up Occupancy Plan
6 | FF&E Report and Procurement Plan
7 | Updated Total Capital Budget (see Appendix B)
8 | Class C Construction Estimate
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 6 Design Development
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 6 REVIEW: DESIGN DEVELOPMENT
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 6 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Design Development Report
3 | Initial Energy Model Report Requirements
4 | Updated Commissioning Plan
5 | Final Total Capital Budget (see Appendix B)
6 | Operating Budgets
7 | Unprotected Operations Budget (see Appendix L)
8 | Class B Construction Estimate
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Gate 6 Approval Procurement
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
GATE 6: APPROVAL FOR PROCUREMENT
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Approved Step 6 FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Complete Gate 6 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
3 | Presentation of latest scope, cost, schedule and risk status
GATE DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the Gate if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
GATE APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Gate.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Associate Deputy Minister
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Executive Director
DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date
Project Executive
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 7 Pre-Construction
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 7 REVIEW: PRE-CONSTRUCTION
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 7 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Construction documents including: a. Copy of tender-ready drawings b. Letter of Confirmation stating that all construction documents and specifications are final and tender ready c. Value Engineering Report including Value Engineering Coversheet (see Appendix O) d. Architect’s Regulatory Agency/Authorities Report
Confirm that construction documents have been submitted to the agencies
3 | Final Total Capital Budget (see Appendix B)
4 | Class A/B Construction Estimate
5 | Written commitment to the Project Sponsor
If General Contract
6 | Tendering Plan
7 | Tendering Schedule
8 | Proposed Construction Schedule
9 | Proposed Process for Soliciting Bids
If Construction Management
10 | Work Package Breakdown
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Gate 7 Approval Construction
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
GATE 7: APPROVAL FOR CONSTRUCTION
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Approved Step 7 FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Complete Gate 7 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
3 | Presentation of latest scope, cost, schedule and risk status
4 | Presentation on procurement process and recommended award
GATE DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the Gate if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
GATE APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Gate.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Associate Deputy Minister
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Executive Director
DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date
Project Executive
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 8 Construction
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 8 REVIEW: CONSTRUCTION
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 8 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Value Engineering Report, including the Value Engineering Coversheet (see Appendix O)
3 | Construction Master Schedule
4 | Updated Commissioning Plan
If General Contract
5 | Recommended General Contractor
6 | Proposed General Contractor Contract
If Construction Management
7 | Recommended Approval of all Work Packages
8 | Tender Analysis for all Recommended Work Packages
9 | Recommended bidders’ Submission
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 9 Construction Update
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 9 REVIEW: CONSTRUCTION UPDATE
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 9 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Household Rough-In Site Visit
3 | Updated Energy Model Report (see Appendix K)
4 | FF&E Detail Report and Budget (see Appendix J)
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 10 Commissioning - Pre-Occ
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 10 REVIEW: COMMISSIONING - PRE-OCCUPANCY
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 10 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Commissioning Pre-Occupancy Preliminary Report
3 | Letter of Completion
4 | Certificate of Substantial Performances
5 | Post-Construction Checklists (see Appendix M)
6 | As-Built Energy Model
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 11 Licensing
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 11 REVIEW: LICENSING
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 11 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Commission the Pre-Occupancy Final Report
3 | Post-Construction Checklists (see Appendix M)
4 | Licensing Inspection
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Gate 11 Approval for Occupancy
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
GATE 11: APPROVAL FOR OCCUPANCY
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | If the Step 10 submissions received a “Conditional Pass” response, ensure all conditions have been met
2 | Approved Step 11 FDAP Step and Gate Forms Submission Checklist (see Appendix A)
3 | Complete Gate 11 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
4 | Presentation of latest scope, cost, schedule and risk status
GATE DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the Gate if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
GATE APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Gate.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Associate Deputy Minister
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Executive Director
DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date
Project Executive
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Step 12 Post-Occupancy
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
STEP 12 REVIEW: POST-OCCUPANCY
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Complete Step 12 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Quarterly Warranty Meetings
3 | Post-Construction Checklists (see Appendix M)
4 | Licensing post-occupancy inspection (3 months)
5 | Mortgage Draw Closeout
6 | Commissioning Final Report
STEP DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
STEP APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Step.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Program Executive
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Project Manager
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12

## Gate 12 Closeout
Department of Seniors and Long-Term Care
Appendix A: FDAP Step and Gate Forms Submission Checklist
Facility Name: |  |  | Checklist Submission Date: |  |  | DD-MMM-YYYY
Submitter's Name: |  |  | Response Due Date: |  |  | DD-MMM-YYYY
Service Provider: |  |  | Project Manager:
GATE 12: Closeout
Deliverables |  |  | Approved |  |  | Comments / References
|  |  | Y | N | N/A
1 | Approved Step 12 FDAP Step and Gate Forms Submission Checklist (see Appendix A)
2 | Complete Gate 12 of the FDAP Step and Gate Forms Submission Checklist (see Appendix A)
3 | Presentation of latest scope, cost, schedule and risk status.
GATE DECISION
| Approved |  |  | <<Please select the appropriate box
Conditional Pass
Fail
Revise and resubmit
Postpone
Cancel
Explain the Reason for the Approved with Comments / Not Approved:
ACTION PLAN
To be completed at the end of the step if project receives a Approved with Comments / Not Approved decision.
Reference | Issue |  | Action Required |  |  |  | Due Date | References
1 | [6 empty] | DD-MMM-YYYY
2 | [6 empty] | DD-MMM-YYYY
3 | [6 empty] | DD-MMM-YYYY
4 | [6 empty] | DD-MMM-YYYY
GATE APPROVAL
Declaration: I confirm that all the identified activities and actions have been completed as required to pass the Gate.
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Service Provider |  |  | Date
Associate Deputy Minister
|  | DD-MMM-YYYY |  |  |  |  | DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date |  | Project Manager |  |  | Date
Executive Director
DD-MMM-YYYY
| Department of Seniors and Long-Term Care | Date
Project Executive
PM Selection
Functional Program
Team Selection
Concept Design
Schematic Design
Design Development
Pre-
Construction
Construction - Structure & Systems
Construction
- Finishes
Commission-ing
Licensing
Post-Occupancy
G6
G0
G4
G12
G11
G7
S1
S2
S4
S5
S7
S8
S9
S10
S11
S3
S6
S12