## Instructions
Department of Seniors and Long-Term Care
Integrated Project Management Package Table of Contents
The Integrated Project Management Package (IPMP) is a consolidated monthly submission that integrates the core project management deliverables and data inputs. The IPMP includes the following core components: (1) Monthly Status Report (MSR), (2) Capital Budget and Expenditures, (3) Risk Register, and (4) Change Control Log. The integrated document minimizes data reprocessing for reporting by drawing on base project data collected within the IPMP. It also facilitates more efficient consolidation of program-level information for reporting within the Department of Seniors and Long-Term Care.
Table of Contents
1.0 MSR | Monthly Status Report (MSR) that summarizes key changes across activities, risk, changes, etc. during the reporting period.
2.0 Capital Budget & Expenditure | Capital Budget & Expenditure template for cost reporting (e.g., budget, actuals, forecast).
2.1 Earned Value Management | Includes cumulative monthly actuals and forecasted financial figures.
3.0 Risk Register | Risk Register template that facilitates the development, monitoring and documentation of a risk management plan, by facilitating a systematic process in identifying risks.
3.1 Risk Matrix | Provides the risk rating to inform the Risk Register.
4.0 Change Log | Change Control Log template that should maintain listing of all changes. Each change request should be logged as it is submitted, with the Change Control Log acting as a central repository throughout the project lifecycle.
Data Formatting Definitions
Example | Field that requires data input.
Example | Field that is linked to another data point in the document. No action required.
Example | Field that is a calculation and subsequent output of data points. No action required.
Status Categories
Red | Worsened compared to last month
Yellow | Remained the same compared to last month
Green | Improved compared to last month

## 1. MSR
Department of Seniors and Long-Term Care
Monthly Status Report
A. PROJECT IDENTIFICATION
Facility Name: |  |  |  |  | Project:
Status Date (YYYY-MM-DD): |  |  |  |  | Status (Step):
Approved Occupancy Date (YYYY-MM-DD): |  |  |  |  | Approved Budget ($CAD):
Overall Status
Status - Current Period: |  | Cost |  | Schedule |  | Scope
Status - Last Period: |  | Cost |  | Schedule |  | Scope
B. ACCOMPLISHMENTS FOR PERIOD
List major task(s) that have been accomplished in this period
1. xxx 2. xxx 3. xxx 4. xxx 5. xxx 6. xxx 7. xxx
C. ACTIVITIES PLANNED FOR NEXT PERIOD
List major task(s) that are schedule to be completed in the coming period
1. xxx 2. xxx 3. xxx 4. xxx 5. xxx 6. xxx 7. xxx
D. MAJOR DELIVERABLES
Input dates, if applicable describe reason for variance
MILESTONES (completion of Step) |  | PLANNED DATE (YYYY-MM-DD) |  | FORECAST DATE (YYYY-MM-DD |  | ACTUAL DATE (YYYY-MM-DD) |  | Reason for Variance
G0. Project Initiation
S1. PM Selection
S2. Project Team Selection
S3. Functional Program
S4. Concept Design
G4. Approval for Detailed Design
S5. Schematic Design
S6. Design Development
G6. Approval for Procurement
S7. Pre-Construction
G7. Approval for Construction
S8. Construction
Mobilization
Structure Start
Weather Tight
S9. Construction Update
FF&E Procurement
Substantial Performance
S10. Commissioning - Pre-Occupancy
S11. Licensing
G11: Approval For Occupancy
Occupancy Date
S12. Post-Occupancy
G12. Closeout
E. RISK MANAGEMENT SUMMARY
List all your risks in the Risk Register. The top 10 by rating will be automatically displayed here.
0 | Total Risks |  | Risk Distribution |  |  |  | Comments
0 | Added Risks |  | This Period |  | Last Period
0 | Retired Risks |  | 0 | Critical |  | Critical
0 | Realized Risks |  | 0 | High |  | High
|  |  | 0 | Medium |  | Medium
|  |  | 0 | Low |  | Low
Risk ID | Risk Name | Rating /Rank | Risk Rating | Date Identified | Owner
0
0
0
0
0
0
0
0
0
0
F. CHANGE REQUEST SUMMARY
List any change requests in the Change Log, any that are Submitted, Contemplated or Pending will be automatically displayed here.
0 | Total # of PCRs |  | Comments
0 | Total Contemplated Change Orders
0 | Total CO's Approved
0 | This Period
PCR | Requestor | Description of Change | Amount Submitted | Change Status
G. COST MANAGEMENT
Input the cost figures on the Capital Budget & Expenditures tab to describe the overall budget of the project.
Summary from 2.0 Capital Budget and Expenditures
| Budget | Actuals + |  | Forecast (Est. to Complete) = |  | Projected Cost |  | Variance (over)/under
Pre-design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land Purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Furnishings & Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total Facility Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Facility Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Value Management Please insert a screengrab of Earned Value Management graphic below.
H. KEY PARTNER COMMUNICATIONS
List major activities / decisions(s) that have occurred this period
Outstanding Partner Communications Share key upcoming consultations, outstanding communications/reviews (e.g., step submission packages) etc.)
I. HEALTH, SAFETY & ENVIRONMENT
List major activities that have been occurred in this period. Please share details of any Time Loss Incidents or accidents which may involve the Department of Labour with the Department within 24 hours of occurrence.
# Meetings Held: |  |  |  | Comments
Average # of People On-Site:
Types of Incidents | Cumulative | This Period
Health &Safety - Near Miss
Health & Safety - Accident
Environmental (e.g., spill or contamination)
Security (e.g., unauthorized personal on site)
| Cumulative | This Period
# of Orientations
J. APPROVAL
By signing this document as submitter, I commit that to the best of my knowledge, this information is accurate.
Submitter - Reviewed and Approved by: |  |  |  |  | Submitter - Endorsed by:

## 2. Capital Budget & Expenditure
Department of Seniors and Long-Term Care
Capital Budget & Expenditure Tracking
Facility:
Location:
Service Provider:
Step Submission:
Date:
|  |  | Beds = |  | Gross Sq Ft =
Date:
| Category | Account | Item | Budget | Actuals + | Forecast (Est. to Complete) = | Projected Cost | Variance (over)/under | Notes
1 | Pre-design | 1.1 | Functional Program |  |  |  | 0 | 0
|  | 1.2 | Consultants |  |  |  | 0 | 0
|  | 1.3 | Site Selection Process |  |  |  | 0 | 0
|  | 1.4 | Site Investigation/survey |  |  |  | 0 | 0
|  | 1.5 | Site Appraisal |  |  |  | 0 | 0
|  | 1.6 | Design Consultant Selection |  |  |  | 0 | 0
|  | 1.7 | Other |  |  |  | 0 | 0
|  | 1.8 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Pre-design | 0 | 0 | 0 | 0 | 0
0%
2 | Design | 2.1 | Design Consultants (Prime) |  |  |  | 0 | 0
|  | 2.2 | Cost Consulting |  |  |  | 0 | 0
|  | 2.3 | Other Consulting |  |  |  | 0 | 0
|  | 2.4 | Site Inspection |  |  |  | 0 | 0
|  | 2.5 | Other |  |  |  | 0 | 0
|  | 2.6 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Design | 0 | 0 | 0 | 0 | 0
0%
3 | Land Purchase | 3.1 | Land Purchase |  |  |  | 0 | 0
|  | 3.2 | Deed Transfer Tax |  |  |  | 0 | 0
|  | 3.3 | Other
|  |  | Total Land Purchase | 0 | 0 | 0 | 0 | 0
0%
4 | Construction | 4.1 | Construction Contracts |  |  |  | 0 | 0
|  | 4.2 | Construction Manager |  |  |  | 0 | 0
|  | 4.3 | Insurances |  |  |  | 0 | 0
|  | 4.4 | Temporary Works |  |  |  | 0 | 0
|  | 4.5 | Other |  |  |  | 0 | 0
|  | 4.6 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Construction | 0 | 0 | 0 | 0 | 0
0%
5 | Project Management | 5.1 | Project Management fees |  |  |  | 0 | 0
|  | 5.2 | Project Staff |  |  |  | 0 | 0
|  | 5.3 | Investigations\Studies |  |  |  | 0 | 0
|  | 5.4 | Legal |  |  |  | 0 | 0
|  | 5.5 | Accounting |  |  |  | 0 | 0
|  | 5.6 | Meeting Expenses |  |  |  | 0 | 0
|  | 5.7 | Travel Expenses |  |  |  | 0 | 0
|  | 5.8 | Other |  |  |  | 0 | 0
|  | 5.9 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Project Management | 0 | 0 | 0 | 0 | 0
0%
6 | Furnishings & Equipment | 6.1 | FF&E Consultants |  |  |  | 0 | 0
|  | 6.2 | Equipment |  |  |  | 0 | 0
|  | 6.3 | Information Technology |  |  |  | 0 | 0
|  | 6.4 | Furnishings |  |  |  | 0 | 0
|  | 6.5 | Draperies |  |  |  | 0 | 0
|  | 6.6 | Shipping |  |  |  | 0 | 0
|  | 6.7 | Storage |  |  |  | 0 | 0
|  | 6.8 | Other |  |  |  | 0 | 0
|  | 6.9 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Furnishing & Equipment | 0 | 0 | 0 | 0 | 0
0%
7 | Start-up | 7.1 | Cleaning - Outsourced |  |  |  | 0 | 0
|  | 7.2 | Security |  |  |  | 0 | 0
|  | 7.3 | Interim Insurance |  |  |  | 0 | 0
|  | 7.4 | Interim Property Taxes |  |  |  | 0 | 0
|  | 7.5 | Moving |  |  |  | 0 | 0
|  | 7.6 | Opening Ceremonies |  |  |  | 0 | 0
|  | 7.7 | Staff Orientation/Training |  |  |  | 0 | 0
|  | 7.8 | Other |  |  |  | 0 | 0
|  | 7.9 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Start-up | 0 | 0 | 0 | 0 | 0
0%
8 | Commissioning | 8.1 | Consultants |  |  |  | 0 | 0
|  | 8.2 | Other |  |  |  | 0 | 0
|  | 8.3 | Contingency (x%) |  |  |  | 0 | 0
|  |  | Total Commissioning | 0 | 0 | 0 | 0 | 0
0%
9 | Sub-Total Facility Costs |  |  | 0 | 0 | 0 | 0 | 0
10 | HST | 14% |  | 0 | 0 | 0 | 0 | 0
11 | HST Rebate |  |  | 0
12 | Estimated Accrued Interest |  |  | 0 | 0 | 0 | 0 | 0
13 | Total Facility Cost |  |  | 0 | 0 | 0 | 0 | 0
Ratios without HST
| Construction Cost/Gsf |  |  | 0 |  |  | 0 | 0
| Construction Cost/Bed |  |  | 0 |  |  | 0 | 0
| Facility Cost/GSF |  |  | 0 |  |  | 0 | 0
| Facility Cost/Bed |  |  | 0 |  |  | 0 | 0

## 2.1 Earned Value Management
Actuals (Cumulative)
| Category | Account | Item | Budget | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01 | 2030-04-01 | 2030-05-01 | 2030-06-01 | 2030-07-01 | 2030-08-01 | 2030-09-01 | 2030-10-01 | 2030-11-01 | 2030-12-01 | 2031-01-01 | 2031-02-01 | 2031-03-01 | 2031-04-01 | 2031-05-01 | 2031-06-01 | 2031-07-01 | 2031-08-01 | 2031-09-01 | 2031-10-01 | 2031-11-01 | 2031-12-01 | 2032-01-01 | 2032-02-01 | 2032-03-01 | 2032-04-01 | 2032-05-01 | 2032-06-01 | 2032-07-01 | 2032-08-01 | 2032-09-01 | 2032-10-01 | 2032-11-01 | 2032-12-01
1 | Pre-design |  | Total Pre-design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Design |  | Total Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Land Purchase |  | Total Land Purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Construction |  | Total Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Project Management |  | Total Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Furnishings & Equipment |  | Total Furnishing & Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Start-up |  | Total Start-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Commissioning |  | Total Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Sub-Total Facility Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast (Est. to complete) - Cumulative
| Category | Account | Item | Budget | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01 | 2030-04-01 | 2030-05-01 | 2030-06-01 | 2030-07-01 | 2030-08-01 | 2030-09-01 | 2030-10-01 | 2030-11-01 | 2030-12-01 | 2031-01-01 | 2031-02-01 | 2031-03-01 | 2031-04-01 | 2031-05-01 | 2031-06-01 | 2031-07-01 | 2031-08-01 | 2031-09-01 | 2031-10-01 | 2031-11-01 | 2031-12-01 | 2032-01-01 | 2032-02-01 | 2032-03-01 | 2032-04-01 | 2032-05-01 | 2032-06-01 | 2032-07-01 | 2032-08-01 | 2032-09-01 | 2032-10-01 | 2032-11-01 | 2032-12-01
1 | Pre-design |  | Total Pre-design | 0
2 | Design |  | Total Design | 0
3 | Land Purchase |  | Total Land Purchase | 0
4 | Construction |  | Total Construction | 0
5 | Project Management |  | Total Project Management | 0
6 | Furnishings & Equipment |  | Total Furnishing & Equipment | 0
7 | Start-up |  | Total Start-up | 0
8 | Commissioning |  | Total Commissioning | 0
9 | Sub-Total Facility Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 3.0 Risk Register
Department of Seniors and Long-Term Care
Risk Register Template
Note: this document will be shared with SLTC for review upon request
Version Date
Identification | [6 empty] | Qualitative Analysis |  |  |  |  | Risk Response |  |  |  | Monitoring & Control |  |  | Issue Management (if required)
Risk ID (#) | Date Identified (MM/DD/YYYY) | Risk Name | Risk Category Select from drop down (e.g., operations) | Description | Cause | Impact Select from drop down (e.g., scope) | Impact Level (1-5) | Probability (1-5) | Risk Score | Level of Risk | Risk Rating | Response Plan | Response Owner | Status Select from drop down (e.g., active) Note: realized risks are Issues | Date of Status (MM/DD/YYYY) | Progress on Action | Risk Owner | Comments | Issue Description | Issue / Risk Realization Date | Impact Level (1-5) | Recommendation | Change Request Ref. #
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 3.1 Risk Matrix
Risk Matrix | [7 empty] | Risk Rating, Response and Action
100% |  |  | converts to Issue (realized risk) |  |  |  |  | Rating | Service Provider / Project Manager Response | Reporting Action
80%+ | Probability | 5 | 5 | 10 | 15 | 20 | 25 | Issue | Active mitigation | Report to the Project Sponsor (weekly status meetings)
60-80% |  | 4 | 4 | 8 | 12 | 16 | 20 | Critical | Treat as facts - must be planned for | Report to the Project Sponsor (weekly status meetings)
40-60% |  | 3 | 3 | 6 | 9 | 12 | 15 | High | Review regularly - require approved mitigation plan | Inform the Project Sponsor (monthly MSR)
20-40% |  | 2 | 2 | 4 | 6 | 8 | 10 | Medium | Actively monitor - require approved mitigation plan | Inform the Project Sponsor (monthly MSR)
<20% |  | 1 | 1 | 2 | 3 | 4 | 5 | Low | Monitor regularly | Monitor at project level
|  |  | 1 | 2 | 3 | 4 | 5
Impact
Schedule Impact |  |  | None | <1m | 1m | 2m | 3m+
Project Cost Impact |  |  | <$10k | 10K-50K | 50K-250K | 250K- 1M | 1M+
Note on I22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update matrix above to info below

## 4.0 Change Log
Department of Seniors and Long-Term Care
Change Control Log
Note: this document will be shared with SLTC for review upon request
<Facility Name>
Service Provider: |  |  | Revision:
Project Manager: |  |  | Last Updated:
[10 empty] | 0 |  |  | 0
PCR No. (#) | Type Select from drop down (e.g., change notice) | Description of Change | Change Cause Select from drop down (e.g., policy) | Change Impact Select from drop down (e.g., scope) | Requester Select from drop down (e.g., scope) | Contractor Name | CCO No. | CO No. | Date Created (MM/DD/YYYY) | Amount Submitted ($CAD) | Schedule Impact Select from drop down (e.g., low) | Change Status Select from drop down (e.g., approved) | Approved Amount ($CAD) | Date Approved (MM/DD/YYYY) | Date of Last Follow-Up (MM/DD/YYYY) | Notes

## Data Validation (hidden)
1.0 - MSR |  |  |  |  | Status (Step)
S1. PM Selection
Status |  |  |  |  | S2. Project Team Selection
Red |  |  |  |  | S3. Functional Program
Yellow |  |  |  |  | S4. Concept Design
Green |  |  |  |  | G4. Approval for Detailed Design
S5. Schematic Design
3.0 - Risk Register |  |  |  |  | S6. Design Development
S7. Pre-Construction
Impact | Level of Risk | Status | Risk Category |  | S8. Construction
Scope | Low | Active | Policy |  | S9. Construction Update
Schedule | Medium | Realized - Issue | Mgmt./Org |  | S10. Commissioning - Pre-Occupancy
Cost | High | Cancelled | Contractor/Vendor |  | S11. Licensing
Quality | Critical | Closed | Site/Zoning |  | S12. Post-Occupancy
Safety |  |  | Cost/Economy/Market
Resources |  |  | Operations
Commercial / Legal |  |  | Technical
Health & Safety
Reputational
Other
4.0 - Change Control Log
Type | Change Impact | Change Cause | Requester | Change Status | Schedule Impact
Change Notice (from contractor/vendor) | Scope | Policy | SLTC | Contemplated | Low
Change Directive (to contractor/vendor) | Schedule | Mgmt./Org | Service Provider | Submitted | Medium
Internal (Service Provider) | Cost | Contractor/Vendor | Project Manager | Pending | High
|  | Cost/Economy/Market | Designer | Approved | Critical
|  | Operations | Contractor | Rejected | Issue
|  | Technical | AHJ | Cancelled
Health & Safety
Other