## Project Plan
Project Plan (Version 2 published on March 2025)
Instructions The table below shows sample project & construction activities and timeline for a general community solar garden project. Insert or delete rows, if needed, to complete a project plan of your community solar project. Fill in the corresponding number of weeks you anticipate each activity to take in the columns to the right.
Phase | Activities | start DD/MM/YY | finish DD/MM/YY | Weeks Required | Project Time Frame (Weeks)
[5 empty] | Year 1 | [25 empty] | Year 2
[5 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104
Example | [insert row to add activities] | insert date | insert date |  | Year 1 2: colour the cells to show duration and timing of each activity
0. Preparation | Read Program Guide |  |  | 4 | bar: Year 1 2 to Year 1 4
| Begin discussions about the project with local decision makers |  |  | 4 | bar: Year 1 4 to Year 1 6
| Create high level project plan |  |  | 1 | bar: Year 1 4
| Hire project management consultant |  |  | 4 | bar: Year 1 4 to Year 1 6
1. Feasibility Studies, Plan and Engagement | Submit Distribution Generator Interconnection Request form to NSPI |  |  | 8 to 24 | bar: Year 1 6 to Year 1 12
| Complete site selection study |  |  | 8 | bar: Year 1 6 to Year 1 12
| Land Acquisition or Lease |  |  | 4 to 8 | bar: Year 1 14 to Year 1 16
| Complete preliminary engineering and geotechnical studies |  |  | 8 to 12 | bar: Year 1 10 to Year 1 16
| Begin community consultation and engagement |  |  | 4 to 48 | bar: Year 1 6 to Year 1 8
| Create Project Budget |  |  | 4 | bar: Year 1 18 to Year 1 20
| Research permit and approval requirements and apply for applicable permits |  |  | 4 | bar: Year 1 18 to Year 1 20
| Identify environmental impacts and create mitigation plan |  |  | 4 | bar: Year 1 22 to Year 1 24
2. Program application | Complete and submit application package |  |  | 12 | bar: Year 1 18 to Year 1 28
3. Acceptance and Program Onboarding | Receive application outcome (approved or declined). If approved, PPA will be awarded and onboarded into the Program. |  |  | 4 to 12 | bar: Year 1 30 to Year 1 32
4. Interconnection Procedures | Continue with Distribution Generator Interconnection Procedures (DGIP)- Distribution System Impact Study (DSIS) Phase |  |  | 12 to 24 | bar: Year 1 40 to Year 1 50
5. Design Phase | Completion of engineering and design |  |  | 4 | bar: Year 1 42 to Year 1 44
| Create procurement strategy |  |  | 4 | bar: Year 1 46 to Year 1 48
| Select solar garden technology |  |  | 4 | bar: Year 1 46 to Year 1 48
6. Construction Phase | Select local contractors |  |  | 4 | bar: Year 1 46 to Year 1 48
| Complete tree clearing and additional geotechnical investigation |  |  | 4 to 24 | bar: Year 2 54 to Year 2 56
| Order materials for distribution upgrades |  |  | 4 to 16 | bar: Year 2 54 to Year 2 56
7. Project Completion | Grid upgrades completed by NSPI |  |  | 4 to 8 | bar: Year 2 62 to Year 2 64
8. Operations and subscriptions | Commence commercial operation |  |  | 4 | bar: Year 2 70 to Year 2 72
| Webpage creation, engage and onboard subscribers |  |  | 8 to 24 | bar: Year 2 62 to Year 2 68

## Financial Planning
Financial Planning Template (Version 2, March 2025)
Project Name
Project Owner(s)
Date
Instructions
1. Obtain all necessary quotes. You are required to attach several quotes as a part of your application package.
2. Complete Sections 1-6 of the template. Each section will assist you with planning your project costs to forecast a proposed power purchase rate.
3. Do not alter green cells. All subtotals and totals in green calculate automatically.
Section 1: Project Budget
Complete the following template with your actual (if already incurred) or projected costs for each line item for your project.
Each cost will not apply to every project. If a line item does not apply to your project, leave the cost as $0.
Include all relevant taxes in each line item.
If you received funding, include the cost you would have incurred for the line item below. You will identify funding and tax credits in Section 2.
| kWdc | kWac | Provided by your engineer in your resource assessment. You are required to attach a copy of your resource assessment to your application package.
Nameplate Capacity
Projected annual net kWhac delivered to the grid | N/A
Project lifetime (years) | 25
Phase 1: Studies & Preparation
Project site selection | 0
Geotechnical study | 0
Preliminary engineering and design | 0
Community engagement | 0
First Nations engagement | 0
Nova Scotia Power- Preliminary Assessment | 0
Environmental assessment, if required (includes solar glare assessment) | 0
Species at risk study | 0
Other- describe | 0 | If you use cells B30-B32, edit the cells A30-A32 to indicate activities that the budget will be spent on.
Other- describe | 0
Other- describe | 0
SUBTOTAL PHASE 1 | 0
Phase 2: Permitting, Design, and Construction | 0
Land acquisition | 0
Land upgrades/site preparation | 0
Municipal and TIR permitting | 0
Final design and engineering | 0
Nova Scotia Power - DSIS | 0
NSPI Interconnection (including grid upgrades) | 0
Legal | 0
PV Modules | 0
Inverters | 0
Foundations | 0
Racking | 0
Piles | 0
Electrical, combiner boxes | 0
Cabling and trenching | 0
Other- describe | 0 | If you use cells B50-B53, edit the cells A50-53 to indicate activities that the budget will be spent on.
Other- describe | 0
Other- describe | 0
Other- describe | 0
Fencing and Security | 0
Installation Costs (including roads, commissioning etc.) | 0
Contingency | 0
SUBTOTAL PHASE 2 | 0
Project management and administration | 0
TOTAL | 0
Section 2: Project Funding
Complete the following table, outlining any funding, grants or tax credits you anticipate or have already received for your community solar project. Provide as much information as possible, and use a separate line for each funding program. You are required to provide confirmation letters of approved or preapproved funding with your application package.
Funding Entity (Government, Department name etc) | Funding Mechanism (program name, tax credit name etc.) | Funding Amount | Status | Item description (ie.g. project site selection, labour, materials)
Total Project Funding |  | 0
Section 3: Project Financing
Complete the following table. If there is one project owner, or the project is owned is a joint venture, complete the first column only (Owner 1).
| Owner 1 | Owner 2
Type of Ownership (e.g. For profit; not-for-profit)
Percent Ownership
Debt Term (e.g. 10, 15, 20 or 25 years)
Debt Interest (Fixed)
Equity ($)
Grants/Funding ($)
Loan ($)
Total Project Loan | 0
Section 4: Operations and Maintenance
Complete the following table, identifying the annual projected costs for line items that are relevant to your project.
Annual Operating Expenses
NSP Subscription Management & Billing | 0 | auto calculated
Land Lease | 0
On site operations/monitoring/maintenance | 0
Project Owner Administration/Coordination/Subscription Management | 0
Insurance | 0
Substation Maintenance, Internet & Snow Clearing | 0
Municipal Tax (incl. property tax) | 0
Total Annual Operations and Maintenance | 0
Section 5: Proposed Power Purchase Rate
1. Considering sections 1-4, and working with your accountant and tax lawyer, complete the table below, providing your proposed power purchase rate for your project.
2. If awarded, your power purchase rate will be the only source of revenue for your project. Your proposed power purchase rate should consider, but is not limited to, the following: funding, grants and tax credits received or planned to receive; all projected expenses such as loan payments, depreciation, operations and maintenance, a decommissiong reserve, and applicable taxes; minimizing or avoiding any cost pressure on rate payers.
3. You are expected to prepare a detailed project budget and forecast with your accountant. The Financial Planning Template is for high level information regarding your program for the purposes of your application, and does not serve as a robost financial planning tool to project your PPA rate.
4. Attach additional information to support your proposed PPA rate.
Proposed power purchase rate ($ per kWh) | 0
Projected net annual energy production (in kWhac) delivered to the grid | 0 | This will be autocalculated based on the information you provide above (C18)
Projected net-income for the life of the project | 0
Projected Return on Equity | 0%
Projected Internal Rate of Return | 0%
Section 6: Consultant and Accountant
Have you consulted with a tax lawyer to ensure you have properly accounted for the Investment Tax Credit in your financial projections?
Have you consulted with an accountant for your project financials?

## Risk Assessment
Risk Assessment Template (Version 2, March 2025)
Start Here: Follow Steps 1 - 3 to complete the risk assessment template. For Step 3, populate the "Risk Assessment Table" below. Do not alter colored cells (Risk Score Table and Risk Severity Score) as it auto populates data.
Step 1: Project information
Project Name
Project Owner(s)
Completed by |  | DO NOT ALTER RISK SCORE TABLE Outcomes populate automatically.
Step 2: Use the following table to complete your risk assessment
Probability 1 - 5 | Impact 1 - 5 |  | Risk Score |  | Count
1 Rare | 1 Insignificant |  | 1 to 5 | NEGLIGIBLE | 0
2 Unlikely | 2 Minor |  | 6 to 10 | MINOR | 0
3 Possible | 3 Moderate |  | 11 to 15 | MODERATE | 0
4 Likely | 4 Major |  | 16 to 20 | HIGH | 0
5 Almost Certain | 5 Severe |  | 21 to 25 | CRITICAL | 0
Step 3: Risk Assessment Table
List project risks you identify in the table below under each relevant category. Assess the likelihood and impact level of each risk and your mitigation plan. Do not alter coloured cells. |  | DO NOT ALTER RISK SEVERITY SCORE CELLS
Category | Risk Factor / Description | Likelihood | Impact | Risk Severity Score | Preventative and Protective Measures
Example: Environment | Infrastructure damage due to weather and natural disasters (flooding, hurricanes, wildfire etc) | 3 | 5 | 15 | Conduct environmental studies, have contingency plans for adverse weather and natural events, have proper insurance etc.
Project Site
0
0
0
0
0
Financial
0
0
0
0
0
Legal
0
0
0
0
0
Procurement and Construction
0
0
0
0
0
Community Support and Engagement
0
0
0
0
0
Environmental Impact
Please speak to negative environmental effects that may result from construction or installation activities at the project site and planned mitigation measures.
0
0
0
0
0
Other
0
0
0
0
0